## Actions 14th Nov 2013
Complete Yes/No
Date Received: Separate Line | Yes
Time: Separate Line | Yes
Reported By: Relate Name,no. email: ( Can have more than one person per site reporting. Keep their details on record) | Yes
Cell no:
Asset Category
Create these categories Electrical,PDM,Building and Plumbing,Airconditioner,Brand Image, Signage , E-Fuel, CCTV, Tank and Line; Automatic Tank Gauging. | Yes
Fault Category eg Lighting, Substation | Yes
Fault Type eg Geyser element - This will be inserted by contractor | Yes
Automatic Tank Gauging
Change “ scope and work” to- Fault Reported | Yes
Create Layout for job card- NJ &SB
Replace “RMC” with “Controller” | Yes
Priority: L M H Emergency ( Add New Field) | Yes
Above + SLA } will automatically give – Timing which the Call Centre Agent can give back to dealer. (Algorithm to written later once Chevron gives SLA) | Yes
Display- Region | Yes
Add one Action Button- “Submit” | Yes
Job card and contractor interface- | Yes
Copy from Engen- except Costing
Also include “Fault Type” eg geyser element
Upload: Job Card-(signed)
Permit(to be developed by Seavest)
: Satisfaction Survey
Upload To happen within 3 days of closing off, or controller gets “pop up” reminder
Rework Job Cards to have suffics “A” “B” “C”- This way we will keep track of work that has to be redone | Yes
Monthly Premium- This will be inputted by Each contractor when they submit a claim for monthly premium.
Each Contractor will have password and username ( Even if he is not a regular contractor) | Yes
Quote submission by contractor= Replace “Internal Notes” with “Quote Overview”
CM ( Seavest Contract Manager) Dashboard when quotes returned
Lowest Bidder ( System Selects)
Seavest recommendation
Chevron recommendation
All three above will be visible to Seavest CM and Chevron.
Devise project plan template- NJ and SB

## Actions 3rd Dec 2013
Complete Yes /No
CALL CENTRE INTERFACE
3 Menu Items | Yes
Log Call | Yes
Repaeat Log | Yes
Search by Site Ref | Yes
Remove Submit Button- After Submitting | Yes
Call Centre agent- Able to Read Job Card
JOB CARD
Change Customer name to Site Name | Yes
Site Number will be the unique ref number set by program code
Change " Contractors Name " to "Technician Name and Surname"
CONTRACTORS INTERFACE
Filter List | Yes
Aknowledge Open | Yes
Notes of initial site contact- Date and time automatic
Once initial site tel call made - Status changes to In Progress
Queued , Inprogress and closed- 3 Separate forms
Jobs can only be closed if permit No inserted
Claim Submission - Invoice uploaded
OUT of Contract- Nicky to devise scope of work form
Request for quote | Yes
Request for definition of scope
Request for extension of SLA