## Simple
Sevest Ref. | Invoice No. | Site Name | Date Logged | Issue / Incident Description | Category | Solution: Reason For ADHOC Billing | #R | Labour Hrs. | Rate | Labour Ttl. | Material Ttl. | Material Description | Mileage (Km) | Mileage Ttl | Inv Excl. | TAX | Inclusive | Approved | Seavest Comments | BP Comments
8099592 | B137 | Chess Service Station | 10 Oct 2017 | cashier and main office roof leaking | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Cordon off working area to make safe and erected mobile scaffold. Prepared problem areas and applied two coats sika raintite and membrane around the electrical box to seal off. , |  | 1 | 400 | 400 | 1050 | Scaffolding (complete with safety signs, guard rails and toe brands), Sika raintite and membrane , | 58 | 493 | 1943 | 272.02 | 2215.02
8099566 | B137 | BP Northdene | 10 Oct 2017 | office ceiling leaking water, very urgently required | Reactive Maintenance | Cordon of work area with metal barricades to make safe. Erected mobile tower scaffold and ascended to the roof to assess. Prepared all problem areas. Applied first coat sika raintite and membrane to affected areas. Allowed to cure before applying second coat. Conducted water test for leaks. Clean up work area and make safe., |  | 1 | 400 | 400 | 1050 | Scaffolding (complete with safety signs, guard rails and toe brands), Sika raintite and membrane , | 62 | 527 | 1977 | 276.78 | 2253.78
8099665 | B137 | BP Bluff | 11 Oct 2017 | door blown off hinges by the storm | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Removed broken door to dispose. Fitted new frame and ledge door and made secure. Applied with primer and allowed to dry. Painted to a neat finish. , |  | 5 | 400 | 2000 | 3838 | External Meranti frame and ledge door , Hinges and screws , Wood primer and paint , | 60 | 510 | 6348 | 888.72 | 7236.72
8100065 | B137 | BP Watercrest | 16 Oct 2017 | Storeroom roof is leaking ... ... | Reactive Maintenance | Cordon of work area with metal barricades to make safe. Erected mobile tower scaffold and ascended to the roof to assess. Prepared all problem areas. Applied first coat sika raintite and membrane to affected areas. Allowed to cure before applying second coat. Conducted water test for leaks. Clean up work area and make safe., |  | 2 | 400 | 800 | 1050 | Scaffolding (complete with safety signs, guard rails and toe brands), Sika raintite and membrane, | 58 | 493 | 2343 | 328.02 | 2671.02
8099604 | B137 | Drive In Motors | 30 Oct 2017 | Auto door is not closing | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Removed and replaced worn return pulley. Re-tension transmission drive belt and reset operator., |  | 1 | 450 | 450 | 2790 | Return pulley including spindle and bearing , | 90 | 765 | 4005 | 560.7 | 4565.7
8100166 | B137 | BP Chatsworth Circle | 30 Oct 2017 | Automatic door is not opening and closing | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Slowed down closing speed to minimise vibration. Quote for recommended major service., |  | 1 | 450 | 450 | 0 | , | 72 | 612 | 1062 | 148.68 | 1210.68
8100315 | B137 | BP Northdene | 30 Oct 2017 | Auto door is not working | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Reprogrammed partial opening to maximum opening., |  | 1 | 450 | 450 | 0 | , | 70 | 595 | 1045 | 146.3 | 1191.3
8098186 | B137 | Moore Rd Service Station | 30 Oct 2017 | Cashier control door not working | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Cordon off working area to make safe. Assessed and found malfunction to power supply. Returned and fitted new 12v power supply unit. Rewire push button release switch. , |  | 1 | 450 | 450 | 1612 | 12 volt supply unit and wiring , 12 volt battery , | 104 | 884 | 2946 | 412.44 | 3358.44
8101530 | B137 | BP Verulam | 30 Oct 2017 | Bullet proof cashier door is loose | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Replaced 3 damaged hinges with new. , |  | 1 | 400 | 400 | 777 | Hinges , | 34 | 289 | 1466 | 205.24 | 1671.24
8098539 | B137 | BP Berea E L | 31 Oct 2017 | Dishwasher pipe is leaking and sink loose | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Replaced damaged dish washer piping. Returned to site and secured the sink to the wall. , |  | 4 | 400 | 1600 | 574.5 | PVC pipe and fittings , Bolt and nuts, | 84 | 714 | 2888.5 | 404.39 | 3292.89
[8 empty] | 18 |  | 7400 | 12741.5 |  | 692 | 5882 | 26023.5 | 3643.29 | 29666.79