## Simple
Sevest Ref. | Invoice No. | Site Name | Date Logged | Issue / Incident Description | Category | Solution: Reason For ADHOC Billing | #R | Labour Hrs. | Rate | Labour Ttl. | Material Ttl. | Material Description | Mileage (Km) | Mileage Ttl | Inv Excl. | TAX | Inclusive | Approved | Seavest Comments | BP Comments
8099463 | B155 | BP Richmond Road | 10 Oct 2017 | Area around public toilet, workshop and goods receiving area water not flowing into drains | Reactive Maintenance | Uplift 6m2 of interlocking paving in the workshop and receiving area and stockpile for reuse. Excavate and deport of site10m3 of failed earthworks. Re-construct layer earthworks by laying 150mm of G5 crusher and compact to 98% MODD AASHTO. Once the G5 crusher is compacted, lay 100mm of G2 crusher and compact to 98% MODD AASHTO. Lay a 10mm river sand and cement binding and reinstate interlocking paving., |  | 16 | 400 | 6400 | 10858 | Compactor, Plaster Sand, NPC Blue Cement, G2 Crusher Run, River Sand, Interlocking Paving, G5 Crusher, | 162 | 1377 | 18635 | 2608.9 | 21243.9
8103555 | B155 | Motorhaven | 24 Jan 2018 | Investigate roof leaks please .. .. .. | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Assessed roof to find which areas were leaking. Could not waterproof leaking areas due to inclement weather conditions. Returned to site and applied two coats sika raintite and membrane to leaking parts of roof, allowing 2 hours drying time between coats., |  | 4 | 430 | 1720 | 1650 | Sika raintite and membrane , | 124 | 1134.6 | 4504.6 | 630.64 | 5135.24
8113193 | B155 | BP Northdene | 30 Jan 2018 | Forecourt drainage is blocked -urgent | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Cordoned off work area to make safe. Unblocked drain using drain rods. Flushed line with a mixture of cleaning agent and water. , |  | 1 | 483.75 | 483.75 | 300 | Drain cleaner , Drain rods, | 52 | 475.8 | 1259.55 | 176.34 | 1435.89
8113184 | B155 | BP John Ross | 31 Jan 2018 | Ceiling in Kitchen needs to be replaced, damage due to water | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Assessed and found hole in Ceiling. Repaired hole and painted repaired ceiling area., |  | 2 | 430 | 860 | 676 | Paint and pollyfiller , Consumables(Paintbrush,sandpaper), | 280 | 2562 | 4098 | 573.72 | 4671.72
8112854 | B155 | BP Madadeni | 31 Jan 2018 | shop, stock room and cashiers office flooded | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Assessed and found gutters blocked with debris. Removed debris and flushed downpipes with water., |  | 2 | 430 | 860 | 0 | , | 350 | 3202.5 | 4062.5 | 568.75 | 4631.25
[8 empty] | 25 |  | 10323.75 | 13484 |  | 968 | 8751.9 | 32559.65 | 4558.35 | 37118