## Simple
Sevest Ref. | Invoice No. | Site Name | Date Logged | Issue / Incident Description | Category | Solution: Reason For ADHOC Billing | #R | Labour Hrs. | Rate | Labour Ttl. | Material Ttl. | Material Description | Mileage (Km) | Mileage Ttl | Inv Excl. | TAX | Inclusive | Approved | Seavest Comments | BP Comments
8130441 | B185 | BP Kwa Mashu Service Station | 16 Jun 2018 | we have identified a leak on the floor at wild bean cafe | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Assessed and found water stains on WBC cupboard base and inside of cupboards. Removed base to inspect for underground leak. Replaced base by glueing back and securing with glue., |  | 2 | 430 | 860 | 280 | Wood glue and dry wall screws, | 20 | 183 | 1323 | 198.45 | 1521.45
8130780 | B185 | New Germany Service Centre | 18 Jun 2018 | The flushing mechanism in the staff male toilet is broken. | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents.Assessed job and will return to site with spares. Returned to site replaced broken flushing mechanism and handle in staff toilet with new. Tested toilet and it is working correctly., |  | 2 | 430 | 860 | 540 | Toilet Mechanism and handle, | 88 | 805.2 | 2205.2 | 330.78 | 2535.98
8131239 | B185 | BP Verulam | 21 Jun 2018 | Cashier kiosk door (BRG) hinge has come off | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Removed door and 3 broken hinges on door. Replaced hinges and resecured it to door and frame with screws and pop rivets. Tested door and it is working correctly. , |  | 3 | 430 | 1290 | 1040 | Heavy duty hinges, Consumables ( Pop rivets, machine screws, drill bit), | 46 | 420.9 | 2750.9 | 412.635 | 3163.54
8131289 | B185 | BP Richmond Road | 21 Jun 2018 | Toilet window came loose from frame. | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Resecured broken aluminuim window hinge to window frame with Pop rivets., |  | 1 | 430 | 430 | 0 | , | 50 | 457.5 | 887.5 | 133.125 | 1020.63
8131391 | B185 | Drive In Motors | 22 Jun 2018 | Large pothole at the entrance to the site - HSSE emergency and can cause damage to customers vehicle | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Removed portion of existing tar and filled with new cold tar , |  | 1 | 430 | 430 | 0 | , | 76 | 695.4 | 1125.4 | 168.81 | 1294.21
8130873 | B185 | Daniels Auto Centre | 02 Jul 2018 | door is holding down when closing,getting jammed by the floor. | Reactive Maintenance | Conducted risk assessment & completed necessary safety documents. Removed door and 3 broken hinges on door. Replaced hinges and resecured it to door and frame with screws and pop rivets. Tested door and it is working correctly. , |  | 2 | 430 | 860 | 995 | Heavy duty hinges, Consumables ( Pop rivets, machine screws), | 174 | 1592.1 | 3447.1 | 517.065 | 3964.17
[8 empty] | 11 |  | 4730 | 2855 |  | 454 | 4154.1 | 11739.1 | 1760.865 | 13499.98